## Net Present Cost
| Project : | xx | [9 empty] | Estimator: | VK
| Location : | xx | [9 empty] | Date: | 2016-01-26
| Currency : | xx | [9 empty] | Rev: | 0
Net Present Cost (NPC) Calculation Template
Typical major onshore oil & gas project
|  |  |  | Duration of plant life | 25 | change as needed
|  |  |  | Indicative average yearly escalation for the overall project CAPEX | 4% | change as needed
|  |  |  | Average OPEX escalation per year | 2.5% | change as needed
|  |  |  | Nominal discount rate for NPC calculation | 10% | change as needed
| CAPEX NPC | [7 empty] | OPEX NPC
| Year (0 = year of estimate) | Indicative CAPEX Spread Money-of-Today (for duration of execution) | CAPEX Annual Escalation | Nominal Discount Rate | Combined Effect on Money-of-Today | NPC as % of Money-of-Today |  |  | OPEX Spread Money-of-Today | OPEX Annual Escalation | Nominal Discount Rate | Combined Effect on Money-of-Today | NPC as % of Money-of-Today
Year of the estimate & approval | 0 |  | 100% | 100% | 100% | 0% |  |  | 0% | 100% | 100% | 100% | 0%
Project start year | 1 | 20% | 104% | 90.91% | 94.55% | 18.91% |  |  | 0% | 102.5% | 90.91% | 93.18% | 0%
| 2 | 40% | 108.2% | 82.64% | 89.39% | 35.76% |  |  | 0% | 105.1% | 82.64% | 86.83% | 0%
Project completion | 3 | 40% | 112.5% | 75.13% | 84.51% | 33.81% |  |  | 0% | 107.7% | 75.13% | 80.91% | 0%
Start of operation | 4 |  | 117% | 68.3% | 79.9% | 0% |  | 1 | 100% | 110.4% | 68.3% | 75.39% | 75.39%
| 5 |  | 121.7% | 62.09% | 75.54% | 0% |  | 2 | 100% | 113.1% | 62.09% | 70.25% | 70.25%
| 6 |  | 126.5% | 56.45% | 71.42% | 0% |  | 3 | 100% | 116% | 56.45% | 65.46% | 65.46%
| 7 |  | 131.6% | 51.32% | 67.53% | 0% |  | 4 | 100% | 118.9% | 51.32% | 61% | 61%
| 8 |  | 136.9% | 46.65% | 63.84% | 0% |  | 5 | 100% | 121.8% | 46.65% | 56.84% | 56.84%
| 9 |  | 142.3% | 42.41% | 60.36% | 0% |  | 6 | 100% | 124.9% | 42.41% | 52.96% | 52.96%
| 10 |  | 148% | 38.55% | 57.07% | 0% |  | 7 | 100% | 128% | 38.55% | 49.35% | 49.35%
| 11 |  | 153.9% | 35.05% | 53.96% | 0% |  | 8 | 100% | 131.2% | 35.05% | 45.99% | 45.99%
| 12 |  | 160.1% | 31.86% | 51.01% | 0% |  | 9 | 100% | 134.5% | 31.86% | 42.85% | 42.85%
| 13 |  | 166.5% | 28.97% | 48.23% | 0% |  | 10 | 100% | 137.9% | 28.97% | 39.93% | 39.93%
| 14 |  | 173.2% | 26.33% | 45.6% | 0% |  | 11 | 100% | 141.3% | 26.33% | 37.21% | 37.21%
| 15 |  | 180.1% | 23.94% | 43.11% | 0% |  | 12 | 100% | 144.8% | 23.94% | 34.67% | 34.67%
| 16 |  | 187.3% | 21.76% | 40.76% | 0% |  | 13 | 100% | 148.5% | 21.76% | 32.31% | 32.31%
| 17 |  | 194.8% | 19.78% | 38.54% | 0% |  | 14 | 100% | 152.2% | 19.78% | 30.1% | 30.1%
| 18 |  | 202.6% | 17.99% | 36.44% | 0% |  | 15 | 100% | 156% | 17.99% | 28.05% | 28.05%
| 19 |  | 210.7% | 16.35% | 34.45% | 0% |  | 16 | 100% | 159.9% | 16.35% | 26.14% | 26.14%
| 20 |  | 219.1% | 14.86% | 32.57% | 0% |  | 17 | 100% | 163.9% | 14.86% | 24.36% | 24.36%
| 21 |  | 227.9% | 13.51% | 30.79% | 0% |  | 18 | 100% | 168% | 13.51% | 22.7% | 22.7%
| 22 |  | 237% | 12.28% | 29.11% | 0% |  | 19 | 100% | 172.2% | 12.28% | 21.15% | 21.15%
| 23 |  | 246.5% | 11.17% | 27.53% | 0% |  | 20 | 100% | 176.5% | 11.17% | 19.71% | 19.71%
| 24 |  | 256.3% | 10.15% | 26.02% | 0% |  | 21 | 100% | 180.9% | 10.15% | 18.36% | 18.36%
| 25 |  | 266.6% | 9.23% | 24.6% | 0% |  | 22 | 100% | 185.4% | 9.23% | 17.11% | 17.11%
| 26 |  | 277.2% | 8.391% | 23.26% | 0% |  | 23 | 100% | 190% | 8.391% | 15.94% | 15.94%
| 27 |  | 288.3% | 7.628% | 21.99% | 0% |  | 24 | 100% | 194.8% | 7.628% | 14.86% | 14.86%
| 28 |  | 299.9% | 6.934% | 20.79% | 0% |  | 25 | 100% | 199.6% | 6.934% | 13.84% | 13.84%
| 29 |  | 311.9% | 6.304% | 19.66% | 0% |  | 26 | 0% | 204.6% | 6.304% | 12.9% | 0%
| 30 |  | 324.3% | 5.731% | 18.59% | 0% |  | 27 | 0% | 209.8% | 5.731% | 12.02% | 0%
| 31 |  | 337.3% | 5.21% | 17.57% | 0% |  | 28 | 0% | 215% | 5.21% | 11.2% | 0%
| 32 |  | 350.8% | 4.736% | 16.62% | 0% |  | 29 | 0% | 220.4% | 4.736% | 10.44% | 0%
| 33 |  | 364.8% | 4.306% | 15.71% | 0% |  | 30 | 0% | 225.9% | 4.306% | 9.726% | 0%
|  | CAPEX Escalation | 9.059% |  | CAPEX NPC | 88.47% | A |  |  |  |  | OPEX NPC | 916.5% | B
Total Net-Present-Cost of CAPEX & OPEX = CAPEX (in Money-of-Today) x A + Yearly OPEX (in Money-of-Today) x B
Notes:
If yearly OPEX is not availbale, then assume around 3% of CAPEX as yearly OPEX for this calculation. (yearly OPEX can vary between 1-5% of CAPEX depending on the project)
NPC is more suitable for cost comparison of different designs. Particularly high CAPEX design Vs. high OPEX design