## Productivity
|  | Project: | xx |  |  | Estimator: | VK
|  | Project Number: | xx |  |  | Date: | 2016-06-26
|  | Location: | xx |  |  | Rev: | 0
Labour Productivity Factor Calculation Tool
to be modified for specific project
EXAMPLE WORKING
Possible additions
1 | Item No. | Factors affecting Labour Productivity | Explanation of factors on Construction Labour Productivities | Project specific supporting comments (to be modified for specific project) | Gulf Coast Norm (not additive) | Effect | Additions for the Current Project (additive) | None | Low | Medium | High | Very High
2 | 1 | Distance of site from population centres. | Offsite traveling time for local labour affects productivity. | Sites are believed to be relatively accessible from population centres | Incl | Low | 0.1 | 0 | 0.1 | 0.2 | 0.3 | 0.4
3 | 2 | Availability of local labour | % of Local labour within the workforce affects productivity. | Local labour is believed to be few | Incl | High | 0.3 | 0 | 0.1 | 0.2 | 0.3 | 0.4
4 | 3 | Skill level of local labour. | % of Local labour requiring training affects productivity. | Local labour is believed to be low-skilled. | Incl | High | 0.3 | 0 | 0.1 | 0.2 | 0.3 | 0.4
5 | 4 | Transport infrastructure at site/region. | Onsite traveling time & complexity will affect productivity. | Transport to/from labour camp is considered average. | Incl | Low | 0.1 | 0 | 0.1 | 0.2 | 0.3 | 0.4
6 | 5 | Climatic conditions at site | Working temperature affects safety and productivity. | Climatic conditions for construction are considered at times to be poor. | Incl | High | 0.3 | 0 | 0.1 | 0.2 | 0.3 | 0.4
7 | 6 | Ground bearing conditions | Ground protection for machinery/plant/personnel/scaffolding affects productivity. | Conditions during winter construction are considered to be poor. | Incl | High | 0.3 | 0 | 0.1 | 0.2 | 0.3 | 0.4
8 | 7 | Water table level | Drainage & sidewall protection of excavations affect productivity. | Conditions are assumed to be very poor. | Incl | Very High | 0.4 | 0 | 0.1 | 0.2 | 0.3 | 0.4
9 | 8 | Permafrost presence & level | Ground insulation & improvement works affect productivities. | No probability of permafrost is considered. | Incl | None | 0 | 0 | 0.1 | 0.2 | 0.3 | 0.4
10 | 9 | Site gradients and terracing | Safety and access may be impeded by such a layout. | Sites are considered to be flat and level. | Incl | None | 0 | 0 | 0.1 | 0.2 | 0.3 | 0.4
11 | 10 | Site layout & congestion at workface | Congestion will affect productivity where site is compact and/or having many vertical structures. | Does not effect new greenfield facilities. Only relevant for brownfield works |  | None | 0 | 0 | 0.1 | 0.2 | 0.3 | 0.4
12 | 11 | Live plant working | Permit control for live plant working affects productivity. | Does not effect new greenfield facilities. Only relevant for brownfield works |  | None | 0 | 0 | 0.1 | 0.2 | 0.3 | 0.4
13 | 12 | Permit control | Permit system complexity and workface access control affect productivity. | Uniform complexity assumed in estimate. | Incl | Low | 0.1 | 0 | 0.1 | 0.2 | 0.3 | 0.4
14 | 13 | Effect of Local bureaucracy / Red Tape | Local bureaucracy effects labour productivity | Uniform complexity assumed in estimate. | Incl | Low | 0.1 | 0 | 0.1 | 0.2 | 0.3 | 0.4
15 | 14 | Messing & accommodation at site | On-site traveling time & complexity will affect productivity. | Sites are considered to have good on-site messing & accommodation access. | Incl | Low | 0.1 | 0 | 0.1 | 0.2 | 0.3 | 0.4
16 | 15 | Material storage at site | Layout and access to storage areas will affect productivity. | Sites are considered to have average distances to material storage areas. | Incl | Medium | 0.2 | 0 | 0.1 | 0.2 | 0.3 | 0.4
17 | 16 | Site security & gate controls | Site access control & complexity will affect productivity. | Access control and security is considered average | Incl | Low | 0.1 | 0 | 0.1 | 0.2 | 0.3 | 0.4
18 | 17 | Site Surveys | Inaccurate / or no data may result in lost productivity due to rework at site | Considered to be average for this project | Incl | Low | 0.1 | 0 | 0.1 | 0.2 | 0.3 | 0.4
19 | 18 | Engineering Package Quality | The quality of the engineering deliverables effects the productivity during construction | This could be variable among different contractors and could be an issue. To be ascertained during bid evaluation | Incl | None | 0 | 0 | 0.1 | 0.15 | 0.2 | 0.25
20 | 19 | Cascading effect | cascading effect of delayed civils work could have affect in the overall productivity if the other subcontracts are mobilised (since civils is the starting point for construction) | This could have an effect for a specific contractor, if proper planning is not in place | Incl | None | 0 | 0 | 0.1 | 0.15 | 0.2 | 0.25
21 | 20 | Schedule | Scheduling decisions could sometimes effect productivity | Lack of solid contracting and procurement strategy could lead to last minute changes to the project execution plan affecting the overall schedule. Working around severe winters, work being started without all drawings being issued for construction could result in redesign and rework | Incl | Low | 0.1 | 0 | 0.1 | 0.15 | 0.2 | 0.25
22 | 21 | Manual Excavation | Normally excavation is assumed to be mechanical. Manual excavation effects the productivity | None assumed for this project |  | None | 0 | 0 | 0.1 | 0.15 | 0.2 | 0.25
23 | 22 | Remote facility standby costs | Standby costs effects productivity | Considered to have an effect for this site | Incl | High | 0.2 | 0 | 0.1 | 0.15 | 0.2 | 0.25
24 | 23 | Construction Contractor | Late involvement of construction contractor in the project may effect productivity | not relevant in this case |  | None | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1
25 | 24 | Reimbursable Contract | Reimbursable contracts have a tendency to have lower productivity due to the nature of the contract | not relevant in this case |  | None | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1
26 | 25 | No previous experience by Contractor | No previous experience in the region by Contractor results in lower productivity | This could be an issue for some contractors |  | None | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1
27 | 26 | War | Any war scenario effects the productivity | This is an issue in some areas of the world. BUT NONE ASSUMED FOR THIS PRODUCTIVITY CALCULATION |  | None | 0 | 0 | 0.5 | 1 | 1.25 | 1.5
28 |  |  | Factor |  | 1 |  | 2.8 | 0 | 3 | 5.45 | 7.65 | 9.85
29
30 |  |  | Productivity Factor |  | 1 |  | 3.8 | 1 | 4 | 6.45 | 8.65 | 10.85
31
32
33 | 27 | Multiple repeatable facilities | The is a learning curve and possibility of sharing resources and optimising schedule if multiple facilities of similar kind are being installed | This is very high in this particular contract as several similar facilities are being built simultaneously |  | Very High | -1 | 0 | -0.25 | -0.5 | -0.75 | -1
|  |  | Revised Productivity Factor |  | 1 |  | 2.8 | 1 | 3.75 | 5.95 | 7.9 | 9.85
IMPORTANT NOTE
This is a personally developed tool to help justify the productivity factor being used in any estimate. The factors, explanations and comments are collected over the years based on innumerable discussions during estimate reviews with different stakeholders. This should only be used as a guide and is not considered perfect or exhaustive.
The presentation and relative effects / additional factors are my own and do not have any industry standard / basis.