## Benchmarking
Project: | XXX | [7 empty] | Prepared By: | VK
Location: | XX | [7 empty] | Date: | 2017-02-18
[9 empty] | Rev: | 0
Thumb Rules for Engineering Costs
Typical Indicative engineering costs for the various projects
Indicative CAPEX for the various projects |  | 100 |  | 200 |  | 500 |  | 600 |  | 1000
| Indicative % of CAPEX | Project 1 | Indicative % of CAPEX | Project 2 | Indicative % of CAPEX | Project 3 | Indicative % of CAPEX | Project 4 | Indicative % of CAPEX | Project 5
Concept work | 0.5% | 0.5 | 0.5% | 1 | 0.2% | 1 | 0.2% | 1.2 | 0.15% | 1.5
Pre-FEED Engineering | 1% | 1 | 1% | 2 | 0.4% | 2 | 0.4% | 2.4 | 0.25% | 2.5
FEED Engineering | 2% | 2 | 2% | 4 | 1.5% | 7.5 | 1.25% | 7.5 | 1% | 10
Detailed Engineering | 7.5% | 7.5 | 6% | 12 | 6% | 30 | 6% | 36 | 3.5% | 35
Procurement services | 2% | 2 | 1.5% | 3 | 1% | 5 | 1% | 6 | 1% | 10
Follow-on Engineering | 1.5% | 1.5 | 1.5% | 3 | 1% | 5 | 1% | 6 | 0.5% | 5
Site Survey Works | 0.5% | 0.5 | 0.5% | 1 | 0.5% | 2.5 | 0.5% | 3 | 0.25% | 2.5
Expected indicative % (of total CAPEX) for all scope | 15% |  | 13% |  | 10.6% |  | 10.35% |  | 6.65%
Expected cost for all scope |  | 15 |  | 26 |  | 53 |  | 62.1 |  | 66.5
Note:
All values are including any project management, project support and other indirect disciplines as required
For most Oil & Gas projects, Engineering costs generally ranges between 5-15% of the overall CAPEX, depending on scope, project size, complexity, brownfield / greenfield etc.
The percentage will be on the lower end for a larger CAPEX and will tend to be on the higher end for smaller CAPEX projects